# Business Case Template

BAHub — BusinessAnalysis.hopto.org

Project / Initiative Name: [                ]

Sponsor: [                ]

BA Author: [                ]

Date: [                ]

Version: [                ]

## 1. Executive Summary

[GUIDANCE] Write for a decision-maker with limited time. Include: the problem, the recommended option, the investment required, the expected return, and the decision needed. Common pitfall: executive summaries that are too long or too technical — target 1 page maximum.

[EXAMPLE] The legacy order management system generates £102,900/year in error rework costs and cannot support planned growth beyond 500 orders/day. The recommended solution is a customer self-service portal integrated with the existing ERP (Option B), requiring a one-time investment of £380,000 with a 12-month payback period and 3-year NPV of £624,000. Approval is sought to proceed to detailed design.

Problem summary (1-2 sentences): [                ]

Recommended option: [                ]

Investment required: [                ]

Expected return / payback: [                ]

Decision required from approvers: [                ]

## 2. Problem Statement

[GUIDANCE] Quantify the current state cost or missed opportunity. Evidence-based problem statements are far more persuasive than qualitative descriptions. Common pitfall: stating the problem in terms of the solution ("we need a new system") rather than the business impact ("we are losing £X/year").

[EXAMPLE] Current order intake process costs the organisation £102,900/year in error rework (8% error rate × 350 orders/day × £35/hr loaded cost, Q3 2025 data). Peak season SLA compliance has fallen to 74% (target: 95%) causing an estimated £45,000 in penalty payments in FY2025. The current system cannot scale beyond 500 orders/day — forecasted demand of 650 orders/day by Q4 2026 will exceed capacity by approximately 30%. Total annual cost of inaction: £147,900 + growing SLA exposure.

Current state cost (quantified): [                ]

SLA/performance impact: [                ]

Growth constraint: [                ]

Total cost of inaction: [                ]

## 3. Options Analysis

[GUIDANCE] Present at least two realistic options including a "do nothing" baseline. Evaluate each against the same criteria. Common pitfall: presenting a preferred option as the only option — decision-makers expect a genuine comparison.

[EXAMPLE] Option A — Do Nothing: Cost £0 upfront, continuing cost £147,900/year. Cannot meet growth demand. Risk: high (further SLA deterioration). Rejected as baseline for comparison only. Option B — Self-Service Portal (Recommended): Upfront cost £380,000, annual saving £147,900, payback 12 months, 3-year NPV £624,000. Fully addresses growth constraint and SLA targets. Option C — Upgrade Legacy System: Upfront cost £220,000, partial error reduction (estimated to £52,000/year saving). Does not resolve growth constraint. 3-year NPV £-64,000 (cost outweighs benefit). Recommendation: Option B.

Option A: Do Nothing: [                ]

Option B: Recommended solution: [                ]

Option C: Alternative: [                ]

Selection rationale: [                ]

## 4. Cost-Benefit Analysis

[GUIDANCE] Include both one-time and recurring costs and benefits. NPV calculation: NPV = Σ(Benefits_t / (1+r)^t) - Initial Investment, where r is the discount rate (typically 10%). Common pitfall: benefit-side double counting and ignoring ongoing maintenance costs.

[EXAMPLE] Costs — One-time: Software licence £120,000; Implementation & integration £180,000; Training £25,000; Project management £55,000. Total one-time: £380,000. Recurring costs: Annual SaaS maintenance £18,000; Support staff retraining (Year 1 only) £8,000. Benefits — Annual: Error rework elimination £102,900; SLA penalties avoided £45,000; Admin redeployment saving £28,000. Total annual benefit: £175,900. Payback: £380,000 ÷ £175,900 = 2.16 years (26 months). 3-year NPV @ 10% discount rate: £175,900×0.909 + £175,900×0.826 + £175,900×0.751 − £380,000 = £624,137.

One-time costs itemised: [                ]

Recurring costs itemised: [                ]

Annual benefits itemised: [                ]

Payback period: [                ]

NPV calculation (show working): [                ]

## 5. Risk Assessment and Mitigation

[GUIDANCE] List the top 5 risks with probability, impact, and mitigation. Risk score = Probability × Impact (1-5 each). Risks scoring >12 should have contingency plans in addition to mitigations. Common pitfall: risks without owners or mitigation actions — unowned risks do not get managed.

[EXAMPLE] RISK-001: ERP API integration complexity underestimated. Probability: 3, Impact: 4, Score: 12. Mitigation: Technical spike (2 weeks) to prototype API integration before full build commences. Owner: IT Lead. Contingency: If integration fails, revert to CSV batch import interim approach. RISK-002: Low user adoption of customer portal. Probability: 2, Impact: 4, Score: 8. Mitigation: User acceptance testing with 20 key customers before go-live; onboarding training for top 50 accounts. Owner: Commercial Director.

RISK-001 (score ≥12, high): [                ]

RISK-002 (score 8-11, medium): [                ]

RISK-003: [                ]

RISK-004: [                ]

RISK-005: [                ]

## 6. Implementation Approach

[GUIDANCE] High-level plan with phases, key milestones, and dependencies. Keep this strategic — detailed project plans belong in a project initiation document. Common pitfall: not identifying dependencies on other projects or initiatives.

[EXAMPLE] Phase 1 (Months 1-2): Technical discovery — API spike, vendor selection, detailed solution design. Phase 2 (Months 3-6): Build and configure — portal development, ERP integration, internal testing. Phase 3 (Month 7): Pilot — 20 selected customer accounts on new portal, parallel run with existing system. Phase 4 (Months 8-9): Full rollout — all customer accounts migrated, legacy process decommissioned. Key dependency: ERP upgrade project (Project Orion) must complete Phase 1 before Month 3 of this project.

Phase 1 (description + duration): [                ]

Phase 2: [                ]

Phase 3 (pilot/UAT): [                ]

Phase 4 (rollout): [                ]

Key dependencies on other projects: [                ]

## 7. Governance Structure

[GUIDANCE] Define who owns the business case outcomes post-implementation. Good governance ensures benefit realisation is tracked. Common pitfall: projects without benefit owners — implementation happens but no one measures whether the forecasted benefits materialised.

[EXAMPLE] Senior Responsible Owner: [Chief Operating Officer name] — accountable for benefit delivery. Project Sponsor: [Operations Director name] — day-to-day business decision authority. Benefits Realisation Owner: [Finance Director name] — measures and reports on NPV and payback achievement quarterly post go-live. Steering Committee: meets monthly during build, quarterly post go-live. Review milestones: 6-month post go-live review (error rate, SLA compliance), 12-month (payback on track), 24-month (NPV verification).

Senior Responsible Owner: [                ]

Project Sponsor: [                ]

Benefits Realisation Owner: [                ]

Governance cadence: [                ]